## 7 October
Project Status Report 1 for 10/7/19
Names: Jason Lubrano, Thomas Alder, Erika Bailon, Sky Ruff, Cassidy Carpenter, Chakrya Ros, Dennis Nguyen, Javier Ramirez
Project Status Report
Project Name:	Eden Crashers, Boulder Apple Tree Project
Date:	7 October 2019		Created By:	Jason Lubrano
Status Rag	Time	Quality	Costs	Risks	Schedule
Progress Last Week	Familiarized ourselves with the technology stack on the project
Progress This Week	Refresh on database design and principles, create a rough database schema for how the operations will workout. Study, read through, and create slides on leaflet documentation and understand the framework behind it. Study, read through, and create slides on Django and the integration behind AngularJS. Create mockups for next meeting with the sponsor. We are in the process of setting up a github workflow.
New Issues, Risks, Impediments, blockers	We may be unfamiliar with some of the technologies used for this project. Not coming to an agreement with our sponsor on the project charter during negoitation. Lataency with feedback and an agreement with the project charter. 7 hours a week may not be enough time to work on this project to complete it in time and reach our milestones and goals. Getting hit by a bus and not having resources and aspects of the project.
Updates on Issues, Risks, Impediments, blockers	N/A

Project Status Report 2 for 10/14/19
Names: Jason Lubrano, Thomas Alder, Erika Bailon, Sky Ruff, Cassidy Carpenter, Chakrya Ros, Dennis Nguyen, Javier Ramirez
Project Status Report
Project Name:	Eden Crashers, Boulder Apple Tree Project
Date:	14 October 2019		Created By:	Cassidy Carpenter
Status Rag	Time	Quality	Costs	Risks	Schedule
Progress Last Week	Refreshed on PostgreSQL and Angular. Assigned tasks to each person to work on for the week.

Progress This Week	We did some team building activites during our last meeting. We also did some retrospect on our last frew meeting and discussed what was going well and what was not. We had people present Django and what they learned while researching Django. Chose a day to present our slides, and split into two teams to create beta mockups and choose which one we like best. Have our github set up and ready to be used as workflow becomes more strenuous.
New Issues, Risks, Impediments, blockers	Time is always an issue when trying to complete a project so we must manage our time especially with the presentations we have this week. We still need to get people more familiar with the technologies used for this project. We need to make sure everyone keeps communicating and people do not become stagnant within the group. Latency between us and the client could still cause problems down the road and we need to always be aware of that.
Updates on Issues, Risks, Impediments, blockers	We are slowly familiarizing ourselves more and more with the different technologies.

Project Status Report 3 for 10/21/19
Names: Jason Lubrano, Thomas Alder, Erika Bailon, Sky Ruff, Cassidy Carpenter, Chakrya Ros, Dennis Nguyen, Javier Ramirez
Project Status Report
Project Name:	Eden Crashers, Boulder Apple Tree Project
Date:	21 October 2019		Created By:	Thomas Alder
Status Rag	Time	Quality	Costs	Risks	Schedule
Progress Last Week	Group has a greater understanding of Django and how it works with Angular from presentations. GitHub was set up to track progress.

Progress This Week	Met and developed our powerpoint presentation for class which we presented on Thursday morning. Started to develop mockups by splitting into two groups and collaborating to create a rough layout on whiteboards. After developing it in separate groups, we came together and compared the ideas/features behind each of our webpages in which we decided to create an electronic version with FIGMA. Once that is done, we can decide as a team what features and the layout of the webpage.
New Issues, Risks, Impediments, blockers	We've now started to develop the look of the interactive map and webpage there is a risk our ideas may not align with the sponsors. We need to continue to research the technologies and their interactions between each other. We have a meeting with the sponsor this coming Tuesday so we need to ensure we convey our ideas and progress appropriately so that the periods in which we don't communicate with the sponsors frequently they know our current progress and what we are working on. Need to divide into frontend/backend teams.
Updates on Issues, Risks, Impediments, blockers	Still need to ensure that people do not become stagnant within the group by dividing out work and hold ourselves/each other accountable. Still slowly familiarizing ourselves with the different technologies.

Project Status Report 4 for 10/28/19
Names: Jason Lubrano, Thomas Alder, Erika Bailon, Sky Ruff, Cassidy Carpenter, Chakrya Ros, Dennis Nguyen, Javier Ramirez
Project Status Report
Project Name:	Eden Crashers, Boulder Apple Tree Project
Date:	28 October 2019		Created By:	Chakrya Ros
Status Rag	Time	Quality	Costs	Risks	Schedule
Progress Last Week	Group has done the first mockup, and presented it to sponsor. The sponsor really liked our mockup, and just asked to modify some filters. More than that, she liked to show this mockup to her team meeting last Thursday after meeing with us.

Progress This Week	Met and assigned Front-end and Back-end team. Both team have to do research on technology to train the whole team. The Front-end will do research on AngularJS. The Back-end team will do research on postgresql and AWS budgeting. These two team will be presented what they learned to the team on next Tuesday. Lead Team also assigned each individual to do project requirement that will be done by next meeting.
New Issues, Risks, Impediments, blockers	Time is still an issue when many work has to be done. Budget for AWS is still not clear. Do not have effectively communication in the team. Most of us did not actively response on the Stack.
Updates on Issues, Risks, Impediments, blockers	Still slowly familiarizing ourselves with the different technologies.

Project Status Report 5 for 11/02/19
Names: Jason Lubrano, Thomas Alder, Erika Bailon, Sky Ruff, Cassidy Carpenter, Chakrya Ros, Dennis Nguyen, Javier Ramirez
Project Status Report
Project Name:	Eden Crashers, Boulder Apple Tree Project
Date:	2 November 2019		Created By:	Erika Bailon
Status Rag	Time	Quality	Costs	Risks	Schedule
Progress Last Week	This week we were able to create a timeline of the entire project to have it ready by April before the expo. Both teams back-end, and front-end presented each their timelines and accordily divided into tasks each step necessary to accomplish the goals of each team. In addition, we assigned to each team memeber an important part of the timeline to be responsible of keeping track of what's being done and responsible of keeping it going to be ready by the deadline. Another things, we split the contents of the technology being used, both teams (fron and back) to make a presentation for next week and the week after.

Progress This Week	We have a good retrospective meeting and the team has been participating more in slack. We have all agreed to be present for all meetings no more zoom meetings. We have been creating calendar events inside slack that sets reminders, so we have a good track of the meetings - locations and times.
New Issues, Risks, Impediments, blockers	The budget hasn't been clarified. We are still waiting on a response about a license to get Figma since right now I only have my account to work on it. Participation of the team when it comes to taking responsabilites is not where we would like it to be.
Updates on Issues, Risks, Impediments, blockers	Still slowly familiarizing ourselves with the different technologies and waiting to hear from the budget decision.

Project Status Report 6 for 11/10/19
Names: Jason Lubrano, Thomas Alder, Erika Bailon, Sky Ruff, Cassidy Carpenter, Chakrya Ros, Dennis Nguyen, Javier Ramirez
Project Status Report
Project Name:	Eden Crashers, Boulder Apple Tree Project
Date:	10 November 2019		Created By:	Javier Ramirez
Status Rag	Time	Quality	Costs	Risks	Schedule
Progress Last Week	We were able to create a timeline of our entire project to have it ready by April. We went over the details and technologies each person on the team would need to be responsible for, we also split back-end and front-end and the team member gave an estimated time when they would have their part finished.

Progress This Week	For this week we went over three presentations from team members. Team members presented how we can use AWS technology and what would be the most benificial parts of AWS and what we should try to stay away from. The teammates also went over AWS budgeting, such as how much it would cost per amazon credit depending on the storage we want. We also presented on PostgreSQL, explained how we can use postgresql to our benifit and how it can work well with other technologies. We also assigned team members with presentations to do next week with different technologies. We also worked on meeting times and locations that's best for everyone for next week.
New Issues, Risks, Impediments, blockers	The budget hasn't been set and stone but we have a rough estimate that we want to try the low end cost of AWS for the time being, then make any adjustments needed, but not all details are exact yet. We are still waiting on a response about a license to get Figma since we only have one account to work on. We are improving on participation of the team, but could still use some work.
Updates on Issues, Risks, Impediments, blockers	Still slowly familiarizing ourselves with the different technologies and still waiting for the budget decision.

Project Status Report 7 for 11/17/19
Names: Jason Lubrano, Thomas Alder, Erika Bailon, Sky Ruff, Cassidy Carpenter, Chakrya Ros, Dennis Nguyen, Javier Ramirez
Project Status Report
Project Name:	Eden Crashers, Boulder Apple Tree Project
Date:	17 November 2019		Created By:	Dennis Nguyen
Status Rag	Time	Quality	Costs	Risks	Schedule
Progress Last Week	We had three presentations last week from different team members on our back end team including presentations on AWS, PostrgreSQL, and AWS budgeting. We assigned additional presentations to team members from the front end team for the following week.

Progress This Week	We all took a personality test and discussed it with each to further understand each other and how it'll affect our project goals. We had a presentation from our front end team on Angular and Leaflet including a demo from both. We did sprint planning this week by assigning tasks to every team member.
New Issues, Risks, Impediments, blockers	The budget hasn't been clarified but we'll estimate for the low end cost of AWS. We are improving on participation of the team, but could still use some work.
Updates on Issues, Risks, Impediments, blockers	Still slowly familiarizing ourselves with the different technologies, figma license is valid, and still waiting for the budget decision.

Project Status Report 8 for 11/24/19 and 12/01/19
Names: Jason Lubrano, Thomas Alder, Erika Bailon, Sky Ruff, Cassidy Carpenter, Chakrya Ros, Dennis Nguyen, Javier Ramirez
Project Status Report
Project Name:	Eden Crashers, Boulder Apple Tree Project
Date:	1 December 2019		Created By:	Sky Ruff
Status Rag	Time	Quality	Costs	Risks	Schedule
Progress Last Week	On the 19th of November we met with our Project Sponsor. In that meeting we discussed stretch goals and how data should be represented and normalized. We also had a meeting with our TA wherin we began preparing our presentation, discussed how to best use our github repo, and discussed the Gantt chart which then got created and pushed to the repo.

Progress This Week	Due to this week being break, little was accomplished. Slides were completed, and AWS was setup rudamentarily.
New Issues, Risks, Impediments, blockers	<uch of the data we would like to have is uncollected.
Updates on Issues, Risks, Impediments, blockers	Still waiting for the budget decision.