## Sheet1
TASK NUMBER	TASK TITLE	TASK OWNER	START DATE	DUE DATE	PCT OF TASK COMPLETE	August:	September:					October:				November:				December:		January:			February:				March:					April:
						Week 1.1	Week 1.2	Week 1.3	Week 1.4	Week 1.5	Week 1.6	Week 1.7	Week 1.8	Week 1.9	Week 1.10	Week 1.11	Week 1.12	Week 1.13	Fall Break	Week 1.14	Week 1.15	Week 2.1	Week 2.2	Week 2.3	Week 2.4	Week 2.5	Week 2.6	Week 2.7	Week 2.8	Week 2.9	Week 2.10	Spring Break	Week 2.11	Week 2.12	Week 2.13	Week 2.14	Week 2.15
0	Front End Design	Erika	10/15/2019	11/9/2019	100								10/15/2019			11/9/2019
0.1	Figma License	Jason	10/15/2019	11/9/1019	100								10/15/2019			11/9/1019
0.2	Figma Design	Erika	10/15/2019	11/9/2019	100								10/15/2019			11/9/2019
0.3	Integrate Design	Sky	10/15/2019	11/9/2019	100								10/15/2019			11/9/2019
1	Front End Build	Erika	11/9/2019	2/25/2020	5												11/9/2019											2/25/2020
1.1	Angular	Thomas, Erika	11/9/2019	1/28/2020	0												11/9/2019							1/28/2020
1.2	Class Design	Thomas, Erika	11/9/2019	12/10/2019	20												11/9/2019				12/10/2019
1.3	Leaflet	Chakrya	11/9/2019	02/11/2020	0												11/9/2019									02/11/2020
1.4	E2E testing	Chakrya	11/9/2019	02/25/2020	0												11/9/2019											02/25/2020
2	Back End Design	Sky	11/9/2019	12/10/2019	80												11/9/2019				12/10/2019
2.1	Clean Data	Cassidy, Chakrya	11/9/2019	11/12/2019	100												11/9/2019	FINISHED
2.2	Postgres Schema	Sky, Cassidy	11/9/2019	11/19/2019	100												11/9/2019		11/19/2019	FINISHED
2.3	Database communication	Cassidy	11/9/2019	12/10/2019	100												11/9/2019				12/10/2019	FINISHED
2.4	AWS design	Sky, Jason	11/9/2019	12/10/2019	100												11/9/2019				12/10/2019	FINISHED
2.5	Data Optimization	Cassidy, Chakrya	11/9/2019	12/3/2019	0												11/9/2019			12/3/2019
3	Back End Build	Sky	12/9/2019	2/25/2020	5																12/9/2019							2/25/2020
3.1	Python API	Jason, Dennis, Javier	12/9/2019	12/21/2019	0																12/9/2019	12/21/2019
3.2	End Point hitting	Erika, Dennis	12/9/2019	2/25/2020	0																12/9/2019							2/25/2020
3.3	AWS Setup	Jason, Sky	12/9/2019	12/25/2019	20																12/9/2019	12/25/2019
3.4	E2e testing	Javier	12/9/2019	2/25/2020	0																12/9/2019							2/25/2020
4	General	Jason	03/01/2020	03/24/2020	0																								03/01/2020			03/24/2020
4.1	Additional E2E testing	Chakrya, Havier	03/01/2020	03/17/2020	0																								03/01/2020		03/17/2020
4.2	General Integration	Dennis, Jason, Erika, Thomas	03/01/2020	03/24/2020	0																								03/01/2020			03/24/2020
5	Deploy	All	03/30/2020	04/01/2020	0																												03/30/2020	04/01/2020